## Sheet1
Task Mode | WBS | Task Name | Duration | Start | Finish | % Complete | Completion Estimate (%) at 4/20/2026 | Completion Estimate (%) at 05/14/2026 | Predecessors | Resource Names | Notes
Auto Scheduled | 1 | Financial / Business Plan | 349 days? | Mon 9/1/25 | Thu 12/31/26 | 31% | Partial | Partial
Auto Scheduled | 1.1 | Transition Operation Planning Activities | 88 days | Mon 9/1/25 | Wed 12/31/25 | 34% | Partial | Partial
Manually Scheduled | 1.1.1 | Identification of Funding - Transition Period | 45 days | Mon 9/1/25 | Fri 10/31/25 | 100% | 100% | 100%
Manually Scheduled | 1.1.2 | Establish Schedule for Staffing / Training | 88 days | Mon 9/1/25 | Wed 12/31/25 | 0% | 75% | 75%
Auto Scheduled | 1.2 | Operations Budgeting - Year 1 | 88 days? | Mon 9/1/25 | Wed 12/31/25 | 60% | Partial | Partial
Manually Scheduled | 1.2.1 | Identification of Funding - Year 1 | 88 days? | Mon 9/1/25 | Wed 12/31/25 | 80% | 80% | 80% |  |  | Awaiting remaining funding commitments
Manually Scheduled | 1.2.2 | Expense Budget Development | 88 days? | Mon 9/1/25 | Wed 12/31/25 | 100% | 100% | 100% |  |  | Original budget development
Manually Scheduled | 1.2.3 | Revised / Refined Expense Budget Development |  |  |  | 0% | 0% | 0% |  |  | LVF working on refined budget; isolating BPC Exps and Revs only
Manually Scheduled | 1.2.4 | Contingency Planning | 88 days? | Mon 9/1/25 | Wed 12/31/25 | 0% | 0% | 0% |  |  | Consider inclusion of budget contingency planning
Auto Scheduled | 1.3 | Operations Budget - Year 2 (Projected) | 132 days | Wed 7/1/26 | Thu 12/31/26 | 0% | Partial | Partial
Manually Scheduled | 1.3.1 | Identification of Funding - Year 2 (Projected) | 132 days | Wed 7/1/26 | Thu 12/31/26 | 0% | 0% | 0%
Manually Scheduled | 1.3.2 | Modification of Service Model |  |  |  | 0% | 0% | 0%
Manually Scheduled | 1.3.3 | Expense Budget Development | 132 days | Wed 7/1/26 | Thu 12/31/26 | 0% | 25% | 25% |  |  | 3yr Model presented 03/02/2026 Agenda; 4% increase
Manually Scheduled | 1.4 | Operations Budget - Year 3 (Planning) |  |  |  | 0% | Partial | Partial
Manually Scheduled | 1.4.1 | Sustainability Considerations and Lessons Learned |  |  |  | 0% | 0% | 0%
Manually Scheduled | 1.4.2 | Modification of Service Model |  |  |  | 0% | 0% | 0%
Manually Scheduled | 1.4.3 | Financial Planning |  |  |  | 0% | 25% | 25% |  |  | 3yr Model presented 03/02/2026 Agenda; 5% increase
Auto Scheduled | 2 | Service Delivery (Workflows & Staff Coverage) | 110 days | Mon 9/1/25 | Fri 1/30/26 | 100% | Complete | Complete
Auto Scheduled | 2.1 | Open Crisis Wing | 110 days | Mon 9/1/25 | Fri 1/30/26 | 100% | Complete | Complete
Auto Scheduled | 2.1.1 | Arrival | 56 days | Mon 9/1/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.1.1.1 | Metal Detector Decision | 4 days | Mon 9/1/25 | Thu 9/4/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.1.2 | Metal Detector Type | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.1.3 | Room Environment | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.1.4 | Customer Service | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.1.5 | Staff Job Responsibilities | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.1.6 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.1.7 | Document Workflow | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Auto Scheduled | 2.1.2 | Registration | 100 days | Mon 9/15/25 | Fri 1/30/26 | 100% | Complete | Complete
Manually Scheduled | 2.1.2.1 | Information Collection Form | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.2 | Credible Registration | 41 days | Mon 9/15/25 | Mon 11/10/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.3 | PCONN Registration | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.4 | ID & Insurance Cards | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.5 | Insurance Verifcation | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.6 | Incoming Calls | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.7 | Accessibility to Guests | 11 days | Mon 9/15/25 | Mon 9/29/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.8 | Staff Job Responsibilities | 41 days | Mon 9/15/25 | Mon 11/10/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.9 | Staff Schedules/Shifts | 100 days | Mon 9/15/25 | Fri 1/30/26 | 100% | 100% | 100%
Manually Scheduled | 2.1.2.10 | Document Workflow | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.1.3 | Crisis Walk In & Emergency Services | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.1.3.1 | Brief Medical Evaluation (Temp; Height; Weight; BP; Pulse/Ox) | 35 days | Mon 9/15/25 | Fri 10/31/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.2 | C-SSRS | 35 days | Mon 9/15/25 | Fri 10/31/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.3 | Comprehensive Assessment / ASAM | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.4 | Crisis Counseling & Resolution (Safety, Harm Reduction, Relapse Prevention) | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.5 | Coordination of Care | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.6 | Peer Support/Recovery Coaching | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.7 | Psychiatric & Medical Consultation | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.8 | Medical Clearance (for higher levels of care) | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.9 | Information & Referral | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.10 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.11 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.3.12 | Document Workflow | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.1.4 | Discharge | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.1.4.1 | Coordination of Care | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.4.2 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.4.3 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.4.4 | Document Workflow | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.1.5 | Post Discharge | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.1.5.1 | Follow Up Activities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.5.2 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.5.3 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.5.4 | Document Workflow | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.1.6 | Special Accomodations | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.1.6.1 | Supports for physical/social/behavioral/environmental challenges | 35 days | Mon 9/15/25 | Fri 10/31/25 | 100% | 100% | 100%
Manually Scheduled | 2.1.6.2 | Document Workflow | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.2 | Secure Crisis Wing | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Auto Scheduled | 2.2.1 | Arrival | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.2.1.1 | Entry | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.1.2 | Safety | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.1.3 | Room Environment | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.1.4 | Customer Service | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.1.5 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.1.6 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.1.7 | Document Workflow | 35 days | Tue 9/30/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.2.2 | Registration | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.2.2.1 | Information Collection Form | 35 days | Tue 9/30/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.2 | Credible Registration | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.3 | PCONN Registration | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.4 | ID & Insurance Cards | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.5 | Insurance Verifcation | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.6 | Incoming Calls | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.7 | Accessibility to Guests | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.8 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.9 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.2.10 | Document Workflow | 35 days | Tue 9/30/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.2.3 | Crisis Walk In & Emergency Services | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.2.3.1 | Brief Medical Evaluation (Temp; Height; Weight; BP; Pulse/Ox) | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.2 | Breathalyzer / UDS if indicated | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.3 | C-SSRS | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.4 | Comprehensive Assessment / ASAM | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.5 | Crisis Counseling & Resolution (Safety, Harm Reduction, Relapse Prevention) | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.6 | Coordination of Care | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.7 | Peer Support/Recovery Coaching | 35 days | Tue 9/30/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.8 | Psychiatric & Medical Consultation | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.9 | Medical Clearance (for higher levels of care) | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.10 | Information & Referral | 35 days | Tue 9/30/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.11 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.12 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.3.13 | Document Workflow | 35 days | Tue 9/30/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.2.4 | Discharge | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.2.4.1 | Coordination of Care | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.4.2 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.4.3 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.4.4 | Document Workflow | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.2.5 | Post Discharge | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.2.5.1 | Follow Up Activities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.5.2 | Staff Job Responsibilities | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.5.3 | Staff Schedules/Shifts | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.5.4 | Document Workflow | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.6 | Special Accomodations | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | Complete | Complete
Manually Scheduled | 2.2.6.1 | Supports for physical/social/behavioral/environmental challenges | 46 days | Mon 9/15/25 | Mon 11/17/25 | 100% | 100% | 100%
Manually Scheduled | 2.2.6.2 | Document Workflow | 35 days | Tue 9/30/25 | Mon 11/17/25 | 100% | 100% | 100%
Auto Scheduled | 2.3 | Withdrawal Management | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | Complete | Complete
Auto Scheduled | 2.3.1 | Arrival | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 2.3.1.1 | Entry | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.1.2 | Safety | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.1.3 | Room Environment | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.1.4 | Body Search | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.1.5 | Customer Service | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.1.6 | Staff Job Responsibilities | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.1.7 | Staff Schedules/Shifts | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.1.8 | Document Workflow | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 2.3.2 | Registration | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 2.3.2.1 | Information Collection Form | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.2 | Credible Registration | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.3 | PCONN Registration | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.4 | ID & Insurance Cards | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.5 | Insurance Verifcation | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.6 | Incoming Calls | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.7 | Accessibility to Guests | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.8 | Staff Job Responsibilities | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.9 | Staff Schedules/Shifts | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.2.10 | Document Workflow | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 2.3.3 | Withdrawal Management Services | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 2.3.3.1 | Staff Job Responsibilities | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.3.2 | Staff Schedules/Shifts | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.3.3 | Document Workflow | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 2.3.4 | Discharge | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 2.3.4.1 | Staff Job Responsibilities | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.4.2 | Staff Schedules/Shifts | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.4.3 | Document Workflow | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 2.3.5 | Post Discharge | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 2.3.5.1 | Staff Job Responsibilities | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.5.2 | Staff Schedules/Shifts | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.5.3 | Document Workflow | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 2.3.6 | Special Accomodations | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 2.3.6.1 | Supports for physical/social/behavioral/environmental challenges | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 2.3.6.2 | Document Workflow | 15 days | Fri 10/31/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 2.4 | Crisis Residential | 80 days | Mon 10/13/25 | Fri 1/30/26 | 100% | Complete | Complete
Manually Scheduled | 2.4.1 | Admission Process from BPC Crisis & Detox | 80 days | Mon 10/13/25 | Fri 1/30/26 | 100% | 100% | 100%
Manually Scheduled | 2.4.2 | Staff Job Responsibilities | 80 days | Mon 10/13/25 | Fri 1/30/26 | 100% | 100% | 100%
Auto Scheduled | 2.5 | Mobile Crisis | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 2.5.1 | <To Be Developed> | 29 days | Mon 10/13/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 3 | Medical Services (Define Practice & Workflow) | 152 days | Mon 9/1/25 | Tue 3/31/26 | 61% | Partial | Partial
Auto Scheduled | 3.1 | Vitals | 145 days | Wed 9/10/25 | Tue 3/31/26 | 61% | Complete | Complete
Manually Scheduled | 3.1.1 | Height | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Manually Scheduled | 3.1.2 | Weight | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Manually Scheduled | 3.1.3 | Blood Pressure | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Manually Scheduled | 3.1.4 | Temperature | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Manually Scheduled | 3.1.5 | Pulse/Ox | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Manually Scheduled | 3.1.6 | Urine Drug Screen | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Manually Scheduled | 3.1.7 | Blood ETOH Level | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Manually Scheduled | 3.1.8 | Breathalyzer | 145 days | Wed 9/10/25 | Tue 3/31/26 | 50% | 100% | 100%
Manually Scheduled | 3.1.9 | Pregnancy Test | 5 days | Wed 9/10/25 | Tue 9/16/25 | 100% | 100% | 100%
Auto Scheduled | 3.2 | Medical Clearance | 49 days | Mon 9/15/25 | Thu 11/20/25 | 54% | Partial | Partial
Manually Scheduled | 3.2.1 | Phlebotomy | 35 days | Mon 9/15/25 | Fri 10/31/25 | 100% | 100% | 100%
Manually Scheduled | 3.2.2 | Lab Work | 49 days | Mon 9/15/25 | Thu 11/20/25 | 75% | 75% |  |  |  | Still in discussion with Doylestown Hospital
Manually Scheduled | 3.2.3 | SMART | 49 days | Mon 9/15/25 | Thu 11/20/25 | 0% | 0% |  |  |  | Targeted to 2027 implementation; Streamlined medical clearance form for transfers between facilities.
Auto Scheduled | 3.3 | Psychiatric Evaluation | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 3.3.1 | Stabilization on Site | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 3.3.2 | Voluntary-201 | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 3.3.3 | Involuntary-302 | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Auto Scheduled | 3.4 | Primary Care | 35 days | Fri 10/3/25 | Thu 11/20/25 | 25% | Partial | Partial
Manually Scheduled | 3.4.1 | Detox | 35 days | Fri 10/3/25 | Thu 11/20/25 | 25% | 50% | 50% |  |  | Need to see if a general medical practice pysician can be hired
Manually Scheduled | 3.4.2 | Other | 35 days | Fri 10/3/25 | Thu 11/20/25 | 25% | 25% | 25% |  |  | Need to see if other parts of the Center can be covered by primary care
Auto Scheduled | 3.5 | Medication | 49 days | Mon 9/15/25 | Thu 11/20/25 | 50% | Partial | Partial
Manually Scheduled | 3.5.1 | ID Bracelets |  |  |  | 0% | 25% | 25% |  |  | Exploring other options
Manually Scheduled | 3.5.2 | Genoa Cubex |  |  |  | 0% | 25% | 90% |  |  | Discussion in progress; need to complete contract / agreement
Manually Scheduled | 3.5.3 | Brought on site | 49 days | Mon 9/15/25 | Thu 11/20/25 | 50% | 100% | 100%
Manually Scheduled | 3.5.4 | Prescribed on site | 49 days | Mon 9/15/25 | Thu 11/20/25 | 50% | 100% | 100% |  |  | Ideas suggested; in discussion phase
Manually Scheduled | 3.5.5 | Medication Administration |  |  |  | 0% | 100% | 100% |  |  | Ideas suggested; in discussion phase
Manually Scheduled | 3.5.6 | Injections | 49 days | Mon 9/15/25 | Thu 11/20/25 | 50% | 100% | 100% |  |  | Ideas suggested; in discussion phase
Manually Scheduled | 3.5.7 | Follow up post discharge | 49 days | Mon 9/15/25 | Thu 11/20/25 | 50% | 100% | 100% |  |  | Need policy and staff assignment
Auto Scheduled | 3.6 | Petitions (302) Part VI Docusign | 0 days | Mon 9/1/25 | Mon 9/1/25 | 0% | Complete | Complete
Manually Scheduled | 3.6.1 | Virtual Signatures |  |  |  | 0% | 100% | 100%
Auto Scheduled | 4 | Care Coordination / Case Management | 35 days? | Mon 12/15/25 | Fri 1/30/26 | 56% | Complete | Complete
Manually Scheduled | 4.1 | Crisis Walk In & Emergency | 35 days | Mon 12/15/25 | Fri 1/30/26 | 50% | 100% | 100%
Manually Scheduled | 4.2 | ASAM | 35 days? | Mon 12/15/25 | Fri 1/30/26 | 50% | 100% | 100%
Manually Scheduled | 4.3 | Withdrawal Management | 35 days | Mon 12/15/25 | Fri 1/30/26 | 50% | 100% | 100%
Manually Scheduled | 4.4 | Crisis Residential | 35 days | Mon 12/15/25 | Fri 1/30/26 | 75% | 100% | 100%
Auto Scheduled | 5 | Medical Emergency | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | Complete | Complete
Manually Scheduled | 5.1 | Crash Cart | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 5.2 | Oxygen | 1 day | Mon 9/15/25 | Mon 9/15/25 | 100% | 100% | 100%
Manually Scheduled | 5.3 | Intravenus (IV) | 1 day | Mon 9/15/25 | Mon 9/15/25 | 100% | 100% | 100%
Auto Scheduled | 6 | Restraints | 35 days | Wed 2/11/26 | Tue 3/31/26 | 100% | Complete | Complete
Manually Scheduled | 6.1 | Physical Restraint Alternatives | 35 days | Wed 2/11/26 | Tue 3/31/26 | 100% | 100% | 100%
Manually Scheduled | 6.2 | Physical Restraint Protocols (if needed) | 35 days | Wed 2/11/26 | Tue 3/31/26 | 100% | 100% | 100%
Auto Scheduled | 7 | Doylestown Hospital (Define Service Delivery Relationship) | 142 days | Mon 9/15/25 | Tue 3/31/26 | 71% | Partial | Partial
Manually Scheduled | 7.1 | 595 Crisis Worker | 142 days | Mon 9/15/25 | Tue 3/31/26 | 75% | 75% | 75% |  |  | Still under review by Doylestown Hospital
Manually Scheduled | 7.2 | Phlebotomy Services | 142 days | Mon 9/15/25 | Tue 3/31/26 | 100% | 100% | 100%
Manually Scheduled | 7.3 | Lab Services | 142 days | Mon 9/15/25 | Tue 3/31/26 | 75% | 75% | 75% |  |  | Still under review by Doylestown Hospital
Manually Scheduled | 7.4 | BPC Clinical Coverage | 142 days | Mon 9/15/25 | Tue 3/31/26 | 50% | 50% | 50% |  |  | LVF trying to get physician coverage
Manually Scheduled | 7.5 | Ambulance EMTALA | 142 days | Mon 9/15/25 | Tue 3/31/26 | 75% | 75% | 100% |  |  | Waiting for regulatory changes
Manually Scheduled | 7.6 | BPC / DH Transfers | 142 days | Mon 9/15/25 | Tue 3/31/26 | 50% | 50% | 50%
Auto Scheduled | 8 | Human Resources | 100 days? | Mon 9/15/25 | Fri 1/30/26 | 91% | Partial | Partial
Auto Scheduled | 8.1 | Job Descriptions (Preliminary) | 95 days | Mon 9/15/25 | Fri 1/23/26 | 94% | Complete | Complete
Manually Scheduled | 8.1.1 | Executive Director | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.2 | Assistant Executive Director | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.3 | Site Coordinator | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.4 | Crisis Worker MHP (includes ASAM Trained) | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.5 | Crisis Worker NonMHP (includes ASAM Trained) | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.6 | D&A Counselor | 49 days | Mon 9/15/25 | Thu 11/20/25 | 75% | 100% | 100%
Manually Scheduled | 8.1.7 | D&A Clinical Supervisor | 49 days | Mon 9/15/25 | Thu 11/20/25 | 75% | 100% | 100%
Manually Scheduled | 8.1.8 | MH Therapist (Co-Occurring) | 49 days | Mon 9/15/25 | Thu 11/20/25 | 75% | 100% | 100%
Manually Scheduled | 8.1.9 | Peer Specialist | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.10 | Peer Specialist Supervisor | 95 days | Mon 9/15/25 | Fri 1/23/26 | 100% | 100% | 100%
Manually Scheduled | 8.1.11 | Recovery Coach | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.12 | Recovery Coach Supervisor | 95 days | Mon 9/15/25 | Fri 1/23/26 | 100% | 100% | 100%
Manually Scheduled | 8.1.13 | Psychiatrist | 49 days | Mon 9/15/25 | Thu 11/20/25 | 75% | 100% | 100%
Manually Scheduled | 8.1.14 | Nurse Practitioner | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.15 | Registered Nurse | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.16 | Psychiatric Technician | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.17 | Residential Aid | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.18 | Receptionist | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.19 | Safety Officer | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.1.20 | Driver/Porter | 49 days | Mon 9/15/25 | Thu 11/20/25 | 75% | 100% | 100%
Auto Scheduled | 8.2 | Staff Coverage (Preliminary) | 49 days | Mon 9/15/25 | Thu 11/20/25 | 88% | Partial | Partial
Manually Scheduled | 8.2.1 | Shifts | 49 days | Mon 9/15/25 | Thu 11/20/25 | 100% | 100% | 100%
Manually Scheduled | 8.2.2 | Schedules | 49 days | Mon 9/15/25 | Thu 11/20/25 | 75% | 75% | 75% |  |  | Need to draft and test.
Auto Scheduled | 8.3 | Job Descriptions | 20 days? | Mon 1/5/26 | Fri 1/30/26 | 0% | Complete | Complete
Manually Scheduled | 8.3.1 | Finalize | 20 days? | Mon 1/5/26 | Fri 1/30/26 | 0% | 100% | 100%
Auto Scheduled | 8.4 | Staff Coverage | 20 days? | Mon 1/5/26 | Fri 1/30/26 | 0% | Not Started | Not Started
Manually Scheduled | 8.4.1 | Finalize | 20 days? | Mon 1/5/26 | Fri 1/30/26 | 0% | 0% | 0%
Auto Scheduled | 9 | Recruitment | 127 days | Mon 1/5/26 | Tue 6/30/26 | 10% | Partial | Partial
Manually Scheduled | 9.1 | On-Call Psychiatry | 127 days | Mon 1/5/26 | Tue 6/30/26 | 10% | 50% | 50% |  |  | Seeking candidates
Manually Scheduled | 9.2 | SUD Physician | 127 days | Mon 1/5/26 | Tue 6/30/26 | 10% | 50% | 50% |  |  | Seeking candidates
Manually Scheduled | 9.3 | CRNP |  |  |  | 0% | 25% | 25% |  |  | Seeking candidates
Manually Scheduled | 9.4 | RN |  |  |  | 0% | 25% | 25% |  |  | Seeking candidates; job fairs in process
Manually Scheduled | 9.5 | Non-Medical Staff |  |  |  | 0% | 25% | 25% |  |  | Seeking candidates; job fairs in process
Auto Scheduled | 10 | Interviewing | 1 day? | Mon 2/2/26 | Mon 2/2/26 | 0% | Partial | Partial
Manually Scheduled | 10.1 | Psychiatry |  | Mon 2/2/26 |  | 0% | 50% | 50%
Manually Scheduled | 10.2 | CRNP |  |  |  | 0% | 25% | 25%
Auto Scheduled | 11 | Hiring | 1 day? | Mon 2/2/26 | Mon 2/2/26 | 0% | Not Started | Not Started
Manually Scheduled | 11.1 | <New Task> |  | Mon 2/2/26 |  | 0% | 0% | 0% |  |  | Can't officially hire until a possible 7/1/2026 opening; need licensure to be able to hire. Hiring will also impact the training schedule below.
Auto Scheduled | 12 | Staff Training Modules | 114 days? | Mon 11/24/25 | Thu 4/30/26 | 99% | Partial | Partial
Manually Scheduled | 12.1 | Program Culture |  |  | Thu 4/30/26 | 0% | 75% | 75%
Manually Scheduled | 12.2 | De-escalation |  |  | Thu 4/30/26 | 0% | 75% | 75%
Manually Scheduled | 12.3 | Position Specific |  |  | Thu 4/30/26 | 0% | 75% | 75%
Manually Scheduled | 12.4 | ASAM | 114 days | Mon 11/24/25 | Thu 4/30/26 | 100% | 100% | 100%
Manually Scheduled | 12.5 | DDAP Required | 114 days | Mon 11/24/25 | Thu 4/30/26 | 100% | 100% | 100%
Auto Scheduled | 13 | Staff Training Schedule | 86 days? | Thu 1/1/26 | Thu 4/30/26 | 0% | Partial | Partial
Manually Scheduled | 13.1 | Existing Staff | 86 days | Thu 1/1/26 | Thu 4/30/26 | 0% | 75% | 75% |  |  | Still in the process of designing training program (moving from concepts to written plan)
Manually Scheduled | 13.2 | New Hires | 86 days? | Thu 1/1/26 | Thu 4/30/26 | 0% | 75% | 75% |  |  | Still in the process of designing training program (moving from concepts to written plan)
Auto Scheduled | 14 | DART | 28 days | Tue 12/9/25 | Thu 1/15/26 | 100% | Complete | Complete
Manually Scheduled | 14.1 | Planning Meeting | 28 days | Tue 12/9/25 | Thu 1/15/26 | 100% | 100% | 100%
Manually Scheduled | 14.2 | DART to Open in Feb2026; Certificate of Occupancy | 28 days | Tue 12/9/25 | Thu 1/15/26 | 100% | 100% | 100%
Manually Scheduled | 14.3 | Bucks County Crisis - Criteria for Admission to DART (Current) | 28 days | Tue 12/9/25 | Thu 1/15/26 | 100% | 100% | 100%
Manually Scheduled | 14.4 | BPC - Criteria for Admission to DART (Future) | 28 days | Tue 12/9/25 | Thu 1/15/26 | 100% | 100% | 100%
Manually Scheduled | 14.5 | BPC Referral Process (Define Process) | 28 days | Tue 12/9/25 | Thu 1/15/26 | 100% | 100% | 100%
Manually Scheduled | 14.6 | BPC / DART Coordination with Police | 28 days | Tue 12/9/25 | Thu 1/15/26 | 100% | 100% | 100%
Auto Scheduled | 15 | First Responders | 54 days? | Thu 1/15/26 | Tue 3/31/26 | 0% | Not Started | Partial
Manually Scheduled | 15.1 | LVF to have early conversations / planning with first responders |  |  | Thu 1/15/26 | 0% | 0% | 75% |  |  | Scheduling first responders for walk-throughs; orientation. We are looking at scheduling a first responder day during the last week of June; The BPC video will be a helpful outreach as well
Manually Scheduled | 15.2 | Establish process / procedure(s) |  |  | Tue 3/31/26 | 0% | 0% | 75%
Auto Scheduled | 16 | Police | 152 days? | Mon 9/1/25 | Tue 3/31/26 | 25% | Partial | Partial
Manually Scheduled | 16.1 | Orientation | 152 days | Mon 9/1/25 | Tue 3/31/26 | 25% | 25% | 75% |  |  | LVF is in active conversations with CB Township and CB Regional police departments; Will be invited to open houses on Wednesdays in June; We are looking at scheduling a first responder day during the last week of June; The BPC video will be a helpful.
Manually Scheduled | 16.2 | Communications | 1 day? | Tue 3/31/26 | Tue 3/31/26 | 25% | 25% | 75%
Manually Scheduled | 16.3 | Relationships |  |  | Tue 3/31/26 | 0% | 0% | 75%
Auto Scheduled | 17 | Ambulance | 1 day? | Tue 3/31/26 | Tue 3/31/26 | 0% | Not Started | Partial
Manually Scheduled | 17.1 | Orientation |  |  | Tue 3/31/26 | 0% | 0% | 75% |  |  | LVF is organizing tour dates for ambulance companies. Likelihood of ambulance transport to BPC has declined due to rigidity of EMTALA.
Manually Scheduled | 17.2 | Communiocations |  |  | Tue 3/31/26 | 0% | 0% | 75%
Manually Scheduled | 17.3 | Relationships |  |  | Tue 3/31/26 | 0% | 0% | 75%
Auto Scheduled | 18 | Credible Configuration (EHR) | 127 days? | Mon 10/6/25 | Tue 3/31/26 | 12% | Partial | Partial
Manually Scheduled | 18.1 | ASAM Document Type | 127 days | Mon 10/6/25 | Tue 3/31/26 | 50% | 75% | 75% |  |  | Working on configuration now through mid June 2026.
Manually Scheduled | 18.2 | Establish process / procedures for recording staff time to cost centers in EHR and in payroll (EDP) | 127 days | Mon 10/6/25 | Tue 3/31/26 | 0% | 0% | 90% |  |  | Same as 18.1
Manually Scheduled | 18.3 | Define documentation for billing to track staff time to cost centers at BPC | 127 days | Mon 10/6/25 | Tue 3/31/26 | 0% | 50% | 90% |  |  | Same as 18.1
Manually Scheduled | 18.4 | Determine new data collection needs | 47 days? | Mon 1/26/26 | Tue 3/31/26 | 0% | 25% | 25% |  |  | Same as 18.1
Manually Scheduled | 18.5 | Develop forms | 47 days? | Mon 1/26/26 | Tue 3/31/26 | 0% | 50% | 50% |  |  | Same as 18.1
Manually Scheduled | 18.6 | Configure medication prescription & administration | 47 days? | Mon 1/26/26 | Tue 3/31/26 | 0% | 25% | 25% |  |  | Same as 18.1
Auto Scheduled | 19 | Contracting & Credentialing | 0 days | Mon 9/1/25 | Mon 9/1/25 | 0% | Not Started | Not Started
Manually Scheduled | 19.1 | Commercial Payers |  |  |  | 0% | 0% | 0%
Auto Scheduled | 20 | Certificate of Occupancy | 1 day? | Tue 3/31/26 | Tue 3/31/26 | 0% | Complete | Complete
Manually Scheduled | 20.1 | <New Task> |  |  | Tue 3/31/26 | 0% | 100% | 100%
Auto Scheduled | 21 | Licensure | 185 days? | Mon 9/1/25 | Fri 5/15/26 | 63% | Partial | Partial
Auto Scheduled | 21.1 | OMHSAS | 1 day? | Fri 5/15/26 | Fri 5/15/26 | 0% | Not Started | Partial
Manually Scheduled | 21.1.1 | Crisis Telephone, Walk In, Emergency Add Location |  |  | Fri 5/15/26 | 0% | 0% | 50% |  |  | Application submitted to OMHSAS
Manually Scheduled | 21.1.2 | Crisis Residential |  |  | Fri 5/15/26 | 0% | 0% | 50% |  |  | Application submitted to OMHSAS
Auto Scheduled | 21.2 | DDAP | 0 days | Mon 9/1/25 | Mon 9/1/25 | 0% | Not Started | Partial
Manually Scheduled | 21.2.1 | Withdrawal Management |  |  |  | 0% | 0% | 50% |  |  | Application submitted to DDAP
Auto Scheduled | 21.3 | BPC Manuals & Documents | 152 days? | Mon 9/1/25 | Tue 3/31/26 | 63% | Partial | Partial
Manually Scheduled | 21.3.1 | MH Service Description | 152 days | Mon 9/1/25 | Tue 3/31/26 | 90% | 90% | 90% |  |  | Still in progress (for internal use for LVF)
Manually Scheduled | 21.3.2 | D&A Service Description | 152 days? | Mon 9/1/25 | Tue 3/31/26 | 75% | 75% | 75% |  |  | Same as 21.3.1
Manually Scheduled | 21.3.3 | General Program (Public) |  |  | Tue 3/31/26 | 0% | 0% | 0% |  |  | Same as 21.3.1
Manually Scheduled | 21.3.4 | MH Regulatory | 152 days? | Mon 9/1/25 | Tue 3/31/26 | 75% | 75% | 75% |  |  | Same as 21.3.1
Manually Scheduled | 21.3.5 | D&A Regulatory | 152 days? | Mon 9/1/25 | Tue 3/31/26 | 75% | 75% | 75% |  |  | Same as 21.3.1
Manually Scheduled | 21.3.6 | LVF P&P | 152 days? | Mon 9/1/25 | Tue 3/31/26 | 0% | 75% | 75% |  |  | Same as 21.3.1
Auto Scheduled | 22 | Facilities | 1 day? | Wed 10/1/25 | Wed 10/1/25 | 44% | Partial | Partial
Manually Scheduled | 22.1 | Building set up for occupancy (will be a large project plan) |  |  |  | 0% | 50% | 100%
Manually Scheduled | 22.2 | Metal Detectors |  | Wed 10/1/25 |  | 50% | 100% | 100%
Manually Scheduled | 22.3 | Security |  |  |  | 0% | 100% | 100%
Manually Scheduled | 22.4 | Safety |  |  |  | 0% | 100% | 100%
Manually Scheduled | 22.5 | Food Service |  | Wed 10/1/25 |  | 25% | 75% | 75% |  |  | Close to agreement with Aramark
Manually Scheduled | 22.6 | Cleaning |  | Wed 10/1/25 |  | 50% | 50% | 50% |  |  | LVF is speaking with current cleaning service fo BPC contract
Manually Scheduled | 22.7 | Transportation |  | Wed 10/1/25 |  | 50% | 50% | 100% |  |  | Vans have been purchased.
Manually Scheduled | 22.8 | Landscaping |  |  |  | 0% | 0% | 90%
Manually Scheduled | 22.9 | Materials/Equipment/Supplies |  |  |  | 0% | 0% | 75%
Auto Scheduled | 23 | MBH Requirements | 217 days? | Mon 9/1/25 | Tue 6/30/26 | 0% | Not Started | Partial
Auto Scheduled | 23.1 | MBH Site Requirements | 217 days? | Mon 9/1/25 | Tue 6/30/26 | 0% | Not Started | Partial
Manually Scheduled | 23.1.1 | Bucks County must provide a letter of support for submission of licensing packet |  |  |  | 0% | 0% | 100%
Manually Scheduled | 23.1.2 | Need date of Certificate of Occupancy from LVF |  |  |  | 0% | 0% | 0% |  |  | Need date of CO from LVF. Magellan does not need to see CO, but it is needed for licensing. Once a license is issued, Magellan can begin credentialing. It is important that all licenses for all programs utilize the same address.
Manually Scheduled | 23.1.3 | Verify exact address and billing information |  |  |  | 0% | 0% | 0% |  |  | This cannot be done until BPC is licensed. The address must be on the license.
Manually Scheduled | 23.1.4 | MBH will need to create MIS# and build record for BPC |  |  |  | 0% | 0% | 0% |  |  | Rendering address, Billing address, NPI, TIN, Phone and Fax #s are needed to create MIS # and record for BPC. Whenever that information is ready, send to Jess T at Magellan and a record will be created within 24 hours.
Manually Scheduled | 23.1.5 | Provide service description to MBH - Telephone and Walk-in |  |  |  | 0% | 0% | 0% |  |  | Submit to Kelly G when prepared, ASAP; MBH will review and respond if edit is needed.
Manually Scheduled | 23.1.6 | Provide service description to MBH - Crisis Residential (Child and Adult) |  |  |  | 0% | 0% | 0% |  |  | Submit to Kelly G when prepared, ASAP; MBH will review and respond if edit is needed.
Manually Scheduled | 23.1.7 | Provide service description to MBH - 3.7 Detox |  |  |  | 0% | 0% | 0% |  |  | Submit to Kelly G when prepared, ASAP; MBH will review and respond if edit is needed.
Auto Scheduled | 23.1.8 | Provide service description to MBH - ASAM Assessment | 0 days | Mon 9/1/25 | Mon 9/1/25 | 0% | Not Started | Not Started
Manually Scheduled | 23.1.8.1 | MBH to confirm which form is to be used; and provide to LVF for completion |  |  |  | 0% | 0% | 0% |  |  | Targeted completion by end of May 2026
Manually Scheduled | 23.1.8.2 | LVF will prepare the SSRC form provided by MBH and return to MBH |  |  |  | 0% | 0% | 0% |  |  | Targeted completion by end of May 2026
Manually Scheduled | 23.1.8.3 | MBH will submit form to SSRC for their approval |  |  |  | 0% | 0% | 0% |  |  | Targeted completion by end of May 2026
Manually Scheduled | 23.1.9 | Supplemental forms - PROMISe Application |  |  |  | 0% | 0% | 0% |  |  | Jess T will send supplemental Promise application to Mary D. for completion. When attestation is signed it will be sent back to Mary to be uploaded with Promise application.
Auto Scheduled | 23.1.10 | MBH PROMISe Enrollment (for each individual service line) | 32 days? | Sat 5/16/26 | Tue 6/30/26 | 0% | Not Started | Not Started
Manually Scheduled | 23.1.10.1 | Mobile Crisis | 33 days? | Sat 5/16/26 | Tue 6/30/26 | 0% | 0% | 0%
Manually Scheduled | 23.1.10.2 | Crisis Emergency | 33 days? | Sat 5/16/26 | Tue 6/30/26 | 0% | 0% | 0%
Manually Scheduled | 23.1.10.3 | Crisis Telephonic | 33 days? | Sat 5/16/26 | Tue 6/30/26 | 0% | 0% | 0%
Manually Scheduled | 23.1.10.4 | Crisis Residential | 33 days? | Sat 5/16/26 | Tue 6/30/26 | 0% | 0% | 0%
Manually Scheduled | 23.1.10.5 | D&A Assessment | 33 days? | Sat 5/16/26 | Tue 6/30/26 | 0% | 0% | 0%
Manually Scheduled | 23.1.10.6 | D&A 3.7 Residential | 33 days? | Sat 5/16/26 | Tue 6/30/26 | 0% | 0% | 0%
Manually Scheduled | 23.1.11 | Licensing on-site visit by OMHSAS will be scheduled (Scott Anstey is point of contact) |  |  |  | 0% | 0% | 0% |  |  | Can licensing be one visit for both (Phone/walkin… and Crisis Res)… or will be done separately?
Manually Scheduled | 23.1.12 | OMHSAS provides MH license |  |  |  | 0% | 0% | 0% |  |  | Get license must be for psych based and phone, crisis res.
Manually Scheduled | 23.1.13 | Contract will be issued once each service secures a license and enrollment |  |  |  | 0% | 0% | 0% |  |  | Only 1 MIS/Credentialing for all services is address aligned.
Manually Scheduled | 23.1.14 | MBH must add the new Crisis Residential location to the BPC contract with MBH |  |  |  | 0% | 0% | 0%
Auto Scheduled | 23.1.15 | D&A also needs to provide credentialing. | 1 day | Mon 9/1/25 | Mon 9/1/25 | 0% | 0% | 0% |  |  | If this is for Magellan credentialing, it’s location based, not service based so as long as the licenses all have the same address, this will aready be done.
Manually Scheduled | 23.1.16 | MBH verifies credentialing is complete |  |  |  | 0% | 0% | 0%
Manually Scheduled | 23.1.17 | MBH must provide "attestation" to add D&A programs for ASAM Assessments and 3.7 Detox |  |  |  | 0% | 0% | 0% |  |  | 3.7WM may not be needed. MitchF will verify.
Manually Scheduled | 23.1.18 | DDAP schedules on-site licensure review. |  |  |  | 0% | 0% | 0%
Manually Scheduled | 23.1.19 | DDAP provides D&A license |  |  |  | 0% | 0% | 0% |  |  | 3.7, and and need state approval for supplemental service (D&A assessment).
Auto Scheduled | 23.2 | MBH Credentialing Process | 0 days? | Mon 9/1/25 | Mon 9/1/25 | 0% | Not Started | Not Started
Manually Scheduled | 23.2.1 | MBH will provide credentialling application to LVF; all BPC services will need to be credentialled at the same location of BPC |  |  |  | 0% | 0% | 0% |  |  | Issued licenses must be exactly the same, per Mitch F.
Manually Scheduled | 23.2.2 | LVF to complete credentialing package and provide to MBH for all services at BPC |  |  |  | 0% | 0% | 0%
Auto Scheduled | 24 | Billing & Accounting | 101 days? | Thu 12/11/25 | Thu 4/30/26 | 0% | Partial | Partial
Manually Scheduled | 24.1 | Billing Protocols - MHDP | 101 days? | Thu 12/11/25 | Thu 4/30/26 | 0% | 50% | 100%
Manually Scheduled | 24.2 | Billing Protocols - MBH | 101 days? | Thu 12/11/25 | Thu 4/30/26 | 0% | 50% | 100%
Manually Scheduled | 24.3 | Billing Protocols - BCDAC | 101 days? | Thu 12/11/25 | Thu 4/30/26 | 0% | 50% | 75%
Manually Scheduled | 24.4 | Billing Protocols - Opioid | 101 days? | Thu 12/11/25 | Thu 4/30/26 | 0% | 50% | 75%
Auto Scheduled | 25 | Information Technology | 174 days? | Mon 9/1/25 | Thu 4/30/26 | 0% | Partial | Complete
Manually Scheduled | 25.1 | Call Routing | 174 days? | Mon 9/1/25 | Thu 4/30/26 | 0% | 100% | 100%
Manually Scheduled | 25.2 | ASAM Document Type | 152 days | Mon 9/1/25 | Tue 3/31/26 | 0% | 100% | 100%
Manually Scheduled | 25.3 | Internal Staff Communications | 174 days? | Mon 9/1/25 | Thu 4/30/26 | 0% | 50% | 100%
Auto Scheduled | 26 | Data Collection & Reporting | 1 day? | Tue 3/31/26 | Tue 3/31/26 | 0% | Partial | Partial
Manually Scheduled | 26.1 | Quality of Care Metrics |  |  | Tue 3/31/26 | 0% | 50% | 75% |  |  | Working on this now; part of form development
Manually Scheduled | 26.2 | Crisis Episode POMS Data |  |  | Tue 3/31/26 | 0% | 50% | 75% |  |  | Trying to automate data exchange with County (PCONN) to streamline process.
Auto Scheduled | 27 | New Policies & Procedures | 0 days | Mon 9/1/25 | Mon 9/1/25 | 0% | Complete | Complete
Manually Scheduled | 27.1 | Metal Detection |  |  |  | 0% | 100% | 100%
Manually Scheduled | 27.2 | Personal Items (prohibited, allowed if secured, securing,, returning) |  |  |  | 0% | 100% | 100%
Auto Scheduled | 28 | Purchasing | 152 days | Wed 10/1/25 | Thu 4/30/26 | 25% | Not Started | Not Started
Manually Scheduled | 28.1 | Medical Equipment | 152 days | Wed 10/1/25 | Thu 4/30/26 | 25% | 0% | 0% |  |  | LVF is preparing shopping list of items needed.
Auto Scheduled | 29 | Public Relations | 0 days | Mon 9/1/25 | Mon 9/1/25 | 0% | Partial | Partial
Manually Scheduled | 29.1 | Furia Rubel Communication Plan |  |  |  | 0% | 50% | 50% |  |  | This is completed and a working document. The “Community Education Plan” has previously been shared.
Manually Scheduled | 29.2 | Video Production |  |  |  | 0% | 50% | 100% |  |  | Shooting video at BPC this week. Should be completed in about 4-6 weeks. The video will be shared with the community on LVF platforms (others are welcome to share too).
Manually Scheduled | 29.3 | Website - Lenapevf.org |  |  |  | 0% | 50% | 50% |  |  | www.lenapevf.org/brightpathcenter is updated and our “hub” of info & FAQ
Manually Scheduled | 29.4 | Print Materials |  |  |  | 0% | 50% | 100% |  |  | BPC initial brochure is in printing. Will be available online and on-site. Development of more detailed print materials for referral sources in process.
Manually Scheduled | 29.5 | Social Media Relations |  |  |  | 0% | 50% | 50% |  |  | Ongoing
Manually Scheduled | 29.6 | Event - Open House Tours |  |  |  | 0% | 50% | 50% |  |  | “Wednesday Walkthroughs” being finalized. I can share the flyer.
Manually Scheduled | 29.7 | Event - VIP Reception |  |  |  | 0% | 50% | 100% |  |  | May 12, 4-7pm. Going to be a great event! Please RSVP. 90+ attendees so far. Media invited
Manually Scheduled | 29.8 | Event - Ribbon Cutting |  |  |  | 0% | 50% | 50% |  |  | TBD. July 1?
Manually Scheduled | 29.9 | Community Outreach |  |  |  | 0% | 50% | 50% |  |  | Ongoing
Manually Scheduled | 29.1 | Define / Conduct "in-person" PR work |  |  |  | 0% | 50% | 50% |  |  | I’m not sure what this is. But FR is working with LVF and media for ongoing PR
Auto Scheduled | 30 | BUDGETING & CONTRACTING ITEMS | 30 days | Mon 2/16/26 | Fri 3/27/26 | 0% | Partial | Partial
Manually Scheduled | 30.1 | Start Budget for SFY26-27 - MH/ID |  |  |  | 0% | 25% | 50%
Manually Scheduled | 30.2 | Start Budget for SFY26-27 - D&A |  |  |  | 0% | 25% | 50%
Manually Scheduled | 30.3 | XYZ Packet (Rate Development for D&A)-CY26-27 | 30 days | Mon 2/16/26 | Fri 3/27/26 | 0% | 25% | 50%
Manually Scheduled | 30.4 | Start Contracts / Amendments - MH/ID - CY26-27 |  |  |  | 0% | 25% | 50%
Manually Scheduled | 30.5 | Start Contracts / Amendments - D&A - CY26-27 |  |  |  | 0% | 25% | 50%
Manually Scheduled | 30.6 | Start Contracts / Amendments - Opioid Settlement Funds - CY26-27 |  |  |  | 0% | 25% | 50%